## Master Tracker
Stage | Governance Pointer | What to Do | Evidence/Artifact | Metric/Threshold | Status | Owner | Due Date | Comments | Link | Last Updated
Casual Analysis and Resolution (CAR) | Problem | Initiated CAR for issues like SLA breaches/defects/ failed PoC | CAR Trigger Log | CAR initiated for all qualifying scenarios |  | CAR Team
|  | Used the 5-WHY template to state the problem in detail | 5-WHY Template | Problem documented with clarity and context
|  | Performed root cause analysis using iterative “Why” questioning | Root Cause Analysis Sheet | Root cause identified and validated
|  | Proposed Corrective Active and Correction Action | Action Plan Template | Actions documented with target dates and owners
|  | Used the 5-WHY template to define corrective and correction actions | 5-WHY Template | Corrective and Correction actions documented
|  | Validated the corrections made for the problem | Validation Report | Effectiveness reviewed and documented
|  | Updated status and documented results comparing before and after | CAR Closure Report | Status updated and CAR item closed
| Positive Outcomes | Identified key drivers behind successful outcomes | Positive Outcome Analysis | Drivers documented and validated
|  | Developed plans to replicate success in other projects | Replication Plan Document | Plan created and approved
|  | Documented and shared lessons learned | Best Practices Repository | Practices shared across relevant teams
|  | Tracked implementation and validate outcomes | Monitoring Log, Validation Report | Replication monitored and validated
|  | Updated status and documented results comparing before and after | CAR Closure Report | Status updated and CAR item closed
Risk & Opportunity Management | Risk Management | Captured Possible Risks(business case, vendor selection, planning, execution) | Risk Log/ Risk Register/ | Risks are identified and documented |  | COE
|  | Rated risks based on probability and impact | Risk Prioritization Matrix | All risks rated and prioritized
|  | Define strategies (avoid, mitigate, exploit, enhance, share, accept) | Response Strategy Document | Response plans documented with owners and timelines
|  | Allocate responsible persons and deadlines for each item | Action Plan Log | 100% risks/opportunities assigned with target dates
|  | Track open items, update status, and close mitigated/leverage items | Risk Watchlist, Status Update Log | Status reviewed and updated for all open items
| Opportunity | Identified possible Opportunities | Opportunity Log | All opportunities evaluated for strategic value
|  | Prioritize opportunities based on cost-benefit analysis | Opportunity Prioritization Matrix | All opportunities evaluated for strategic value
Vendor Selection | Defining Objectives and Scope | Created a detailed SOP mentioning the need for Vendor Onboarding | SOP Document | Objective and Scope Approved |  | COE
| Identify prospective vendors | Referred to the Vendor Directory to identify prospective Vendors | Vendor List | All prospect Vendors listed
| Ringi Approval | RFP Ringi Floated | Ringi Initiation Communication | Ringi is floated
| Float RFP/RFQ | Issued RFP to shortlisted vendors; include scope, timelines, compliance, and evaluation criteria | RFP document | RFP sent to all shortlisted vendors
|  | Created Technical Evaluation Sheet for shortlisting as per DAR Process | DAR Document/Technical Evaluation Sheet | DAR Document Created
|  | Shortlisted Vendors For RFQ based on Technical Evaluation for Commercials | Shortlist Approval Log | Minimum 3 vendors shortlisted
|  | Requested detailed commercial quotes from the shortlosted vedors | RFQ Document | RFQ sent to all shortlisted vendors
|  | Shortlisted Vendors For RFQ based on Technical Evaluation for Commercials | Shortlist Approval Log | Minimum 3 vendors shortlisted
| Review proposals | Collected and reviewed proposals for completeness, compliance, and alignment with requirements | Proposal evaluation sheet | 100% proposals reviewed
| Shortlist vendors | Scored vendors based on solution quality, compliance, and risk; document rationale | Evaluation matrix | Shortlist approved by governance
|  | Evaluated vendors on technical criteria (architecture, scalability, integration, etc.) | Technical evaluation matrix | Evaluation completed for all shortlisted vendors
|  | Evaluated vendors on cost, licensing, support | Commercial evaluation sheet | Commercial score documented
|  | Invited shortlisted vendors to present their solution to senior management | Presentation deck, MoM | 100% shortlisted vendors presented
|  | Used Decision Analysis & Resolution (DAR) template to score vendors across defined criteria | DAR evaluation sheet | DAR applied for all vendors
|  | Mark vendors as “Qualified” based on combined technical + commercial score and presentation | Qualification log | Qualification decision documented
| Sign a Contract with the Vendor | Confirm vendor selection based on evaluation and presentation | Selection note | Selection rationale documented
|  | If POC was required, evaluate vendor performance and raise PO if chargeable | POC report, PO copy | POC evaluation completed
|  | Vendor prepared SoW/Contract received based on RFI/RFP/proposal | Draft SoW/Contract | Draft received from vendor
|  | Finalized scope, deliverables, commercials, and terms after negotiation | Final SoW/Contract | Final version approved by both parties
|  | Ensured NDA is signed between vendor and MSIL DE | Signed NDA | NDA signed before contract
|  | Get contract reviewed by legal teams of both vendor and MSIL DE | Legal review note | Legal review completed
|  | Obtained internal approvals via Ringi and management sign-off | Ringi approval, sign-off email | Approval obtained before PO
|  | Raised Purchase Order or Agreement in system and archive signed contract | PO copy, signed contract | PO raised and archived
| Monitoring and Performance Evaluation | Tracked vendor performance against agreed cost, quality, and time metrics | KPI Dashboard, SLA Tracker | 100% KPIs/SLA tracked as per governance process
|  | Used defined metrics and governance framework for evaluation | Metrics and Governance Document | Metrics aligned with governance standards
|  | Evaluated vendor performance using formal criteria | Vendor Performance Evaluation Matrix | Evaluation completed at defined intervals
|  | Shared feedback with vendor and track action items | Feedback Form, Action Item Tracker | Feedback shared and actions monitored
|  | Documented vendor performance and lessons learned | Retrospective Notes, Repository Update Log | Repository updated post-evaluation
POC Creattion | Plan for PoC | Document the problem statement, objectives, and expected outcomes | PoC Plan Document | Objectives clearly defined and approved |  | COE
|  | Defined measurable success and performance indicators for PoC | Success Criteria Checklist | Criteria documented and agreed upon |  | COE
|  | Identified functional needs and user acceptance parameters | Functional Requirements Doc | All key functional/user aspects covered |  | COE
|  | Investigate existing or COTS solutions | Solution Assessment | Minimum 1 viable existing solution explored |  | COE
|  | Vendor Selection Process Followed? | Vendor Selection Purchase Order | Vendor Onbaorded |  | COE
| Conduct PoC | Execute PoC with shortlisted vendors to validate feasibility | PoC Execution Report | PoC completed for all shortlisted vendors |  | COE
|  | Use feasibility checklist to evaluate PoC outcomes | Feasibility Assessment Sheet | Feasibility documented and reviewed |  | COE
| Business Case Refinement | Organize workshops with partners to refine business case and strategy | Workshop MoMs, Presentations, Reports | Minimum 2 workshops conducted with documented outcomes |  | COE
|  | Consolidate workshop inputs into a formal business strategy document | Business Strategy Document | Document approved by stakeholders |  | COE
|  | Update effort estimates and ROI based on refined business case | Revised Estimation Sheet, ROI Analysis | ROI and effort estimates updated and validated |  | COE, Vendor
|  | Create a roadmap outlining key milestones, timelines, and dependencies for PoC execution | Roadmap Document | Roadmap reviewed and approved by governance |  | COE, Vendor
| PoC sign-off | Secure formal approval for PoC execution based on success criteria | PoC Sign-off Document | Sign-off received from all required stakeholders |  | COE, Vendor
|  | Raise demand for resources or budget if needed for PoC execution | Demand Request Form | Demand raised and approved (if applicable) |  | COE
Development | Define | Vendor Selection Process Followed? | Vendor Selection Purchase Order | Vendor Onbaorded |  | COE
|  | Define product vision, goals, and high-level features with Vendor | Product Roadmap Document | Roadmap approved by stakeholders |  | COE
|  | Documented functional and non-functional requirements in a detailed BRD | Detailed BRD | BRD reviewed and signed off |  | COE
|  | Designed business, application, and data architecture | Architecture Document | Architecture reviewed and approved |  | COE, Vendor, EA
|  | Created Technical Evaluation Sheet for Architecture Selection as per DAR Process | DAR Document | DAR Document Created |  | COE, Vendor, EA
|  | Prepared infrastructure for development, UAT, and integration testing | Environment Setup Checklist | Environments ready before sprint initiation |  | COE, Vendor
|  | Planned sprints based on prioritized user stories and roadmap | Sprint Plan Document | MVP sprint plan approved and baselined |  | Vendor
| Design | Used T-Shirt sizing or Fibonacci series to estimate effort | Estimation Sheet | 100% user stories estimated using approved techniques |  | Vendor
|  | Listed all features and functional requirements as user stories | Product Backlog Document | Backlog includes all planned features |  | COE, Vendor
|  | Created a time-boxed sprint for 2-4 weeks weeks with goal of what is to be built, design and deliver at the end of sprint. | Sprint Plan | Sprint plan approved and baselined |  | COE, Vendor
|  | Refine stories with acceptance criteria and NFRs | Groomed Backlog, Story Cards | 100% stories groomed before sprint start |  | COE, Vendor
|  | Secure User Story Approval over the Product Backlog | User Story Approval | All sprint stories approved by product owner |  | COE, Vendor
|  | Designed wireframes/Assessed impact on systems, code, and data | Wireframes, Impact Analysis Report | Designs reviewed and impact documented |  | COE, Vendor
|  | Identify reusable components to optimize development | Reuse Library Reference | Reuse documented and approved |  | COE, Vendor
|  | MSIL Coding Standards/Guidelines were shared with the Developers/Vendors | Email communication shared with vendor | All code reviewed before testing |  | COE, Vendor
|  | Developed all features according to the approved user stories | Logs of Code Repositories | 100% stories developed and committed |  | COE, Vendor
|  | Code was reviewed as per Quality and Security Standards | Code Review Checklist | All code reviewed before testing |  | COE, Vendor
|  | Conducted Unit testing for individual components | Unit Test Report | 100% code units tested |  | COE, Vendor
|  | Validated end-to-end functionality and system interactions | SIT Report | All interfaces tested and verified |  | COE, Vendor
|  | Tracked and resolved defects during testing | Defect Log, Fix Report | 100% critical defects resolved before demo |  | COE, Vendor
|  | Performed RCA for defects identified in UAT as per CAR process | CAR Document/Closure Report/RCA Document | CAR Document Created |  | COE, Vendor
|  | Presented completed stories to stakeholders for feedback | Sprint Demo Deck, Feedback Log | Demo conducted and feedback captured |  | COE, Vendor
|  | Provided effort estimation for changes | Effort Estimation Sheet | Estimation validated by technical team |  | COE, Vendor
|  | Conducted Sprint Retrospective- Reviewed outcomes and identified improvements | Retrospective Report | Retrospective completed and actions documented |  | COE, Vendor
|  | Define sprint-wise delivery plan for MVP | MVP Sprint Plan | MVP plan approved and aligned with roadmap |  | COE, Vendor
| UAT, VAPT, AI Risk Assessment | Executed User Acceptance Testing with COE and user involvement based on Test Cases | UAT Report | UAT completed and signed off |  | COE, Vendor
|  | Track and resolve defects identified during UAT | UAT Defect Log, Closure Report | 100% critical defects closed before VAPT |  | COE, Vendor
|  | Performed RCA for defects identified in UAT as per CAR process | CAR Document/Closure Report/RCA Document | CAR Document Created |  | COE, Vendor
|  | Conducted VAPT | VAPT Report | UAT completed and signed off |  | COE, Vendor
|  | Performed RCA for defects identified in VAPT as per CAR process | CAR Document/Closure Report | CAR Document Created |  | COE, Vendor
|  | Conducted AI Risk Assessment (If Applicable) | AI Risk Assessment Report | AI committee has provided AI Risk Sign-off |  | COE, Vendor
|  | Mitigated AI risks highlighted in AI Risk Assessment (If Applicable) | Closure Report | All AI Related Risks have been mitigated |  | COE, Vendor
|  | Secured formal sign-off and deploy changes to production | Sign-off Document, Deployment Logs | Sign-off received and deployment completed |  | COE, Vendor
| Release | Referred to Release Checklist for validation of release readiness | Release Checklist Audit Report | Audit passed before deployment |  | COE, Vendor
|  | Created and circulated a Release Note | Release Note | Release Noted is created |  | COE
DEPLOYMENT BY RELEASE TEAM
| Post Go Live Support | Tracked defects post go-live as per support process | Go-Live Defect Log | All go-live defects logged and tracked |  | COE, Vendor
|  | Gather feedback and analyze for future improvements | Feedback Report, Analysis Summary | Feedback analyzed and actions identified |  | COE, Vendor
Support/HyperCare | Service Request | Logged a Service Request Ticket with required details | SR Log | 100% SRs logged |  | Support L1
|  | SRs are assigned to L1 for initial assessments | Assignment Log/Zendesk Ticket Logs | 100% tickets assigned within SLA |  | Support L1
|  | Determined Urgency and Impact of the SRs/ Created Priority Matrix | Priority Matrix | Priority assigned to all tickets |  | Support L1
|  | Resolved SRs based on known Solutions/ KEDB Referred? | Resolution Log/RCA Document | Known solution applied and user informed |  | Support L1
|  | Allowed 24 Hour Cooling period/ Allowed user to re-open the Ticket | ?? | Reopened tickets reassigned to L1 |  | Support L1
|  | Escalated the SR to L2 in case no known solution is available | Escalation Log/ Zendesk Logs | 100% unresolved tickets escalated to L2 |  | Support L2
|  | Secured formal approval from manager for the new solution before implementation | Approval | All new solutions reviewed and approved |  | Support L2
|  | KEDB updated with new solution? | KEDB Documents | KEDB created for all new solutions |  | Support L2
|  | Ticket closed with proper RCA/RCA Document Created? | Resolution Log/RCA Document | New Solution applied and Informed User |  | Support L2
|  | Triggered Change Request process for Major Config/Code Changes | Change Request Form | CR initiated for all qualifying service requests |  | COE Support
| Incident | Logged the Incident Ticket with required details | Incident Log | 100% Incidents logged |  | Support L1
|  | Incidents are assigned to L1 for initial assessments | Assignment Log/Zendesk Ticket Logs | 100% tickets assigned within SLA |  | Support L1
|  | Determined Urgency and Impact of the Incidents/ Created Priority Matrix? | Priority Matrix | Priority assigned to all tickets |  | Support L1
|  | Checked if the error is a Recurrring Major Incident/ Referred recurring issues to Problem Management? | Problem Management Referral Log/ CR Log? | 100% recurring incidents referred |  | Support L1
|  | Resolved Incidents based on known Solutions/ KEDB Referred? | Resolution Log/RCA Document | Known solution applied and user informed |  | Support L1
|  | Allowed 24 Hour Cooling period/ Allowed user to re-open the Ticket | ?? | Reopened tickets reassigned to L1 |  | Support L1
|  | Escalated the Incident to L2 in case no known solution is available | Escalation Log/ Zendesk Logs | 100% unresolved tickets escalated to L2 |  | Support L2
|  | Secured formal approval from manager for the new solution before implementation | Approval | All new solutions reviewed and approved |  | Support L2
|  | KEDB updated with new solution? | KEDB Documents | KEDB created for all new solutions |  | Support L2
|  | Ticket closed with proper RCA/RCA Document Created? | Resolution Log/RCA Document | New Solution applied and Informed User |  | Support L2
|  | Allowed 24 Hour Cooling period/ Allowed user to re-open the Ticket | ?? | Reopened tickets reassigned to L1 |  | Support L2
|  | Escalated the Incident to L3 in case L2 is not able resolve, Implemented immediate workaround, Testing | Zendesk escalation logs, Workaround implementation | Workaround implemented, tested and user informed |  | Support L3
|  | Transferred the Incident to Dev team in case of major code/config changes | Zendesk Logs | Permanent fix initiated for major issues |  | Support L3
|  | Triggered Change Request process for Major Config/Code Changes | Change Request Form | CR initiated for all qualifying Incidents |  | COE Support
| Change Request | Logged the Change Request with required details | Change Request Form | 100% CRs logged in system
|  | Assessed the impact on code, DB objects, and impacted systems | Impact Analysis Report | All impacted components documented
|  | Provided effort estimation for change implementation | Effort Estimation Sheet | Estimation validated by technical team
|  | Made the necessary updates and track changes | Code change logs | 100% changes tracked and versioned
|  | Performed Unit Testing for individual components for correctness | Unit Test Report | 100% code units tested
|  | Validated system-level functionality after changes | System Test Report | All system functions tested
|  | Executed UAT and VAPT with user and COE | UAT Report, VAPT Report | UAT/VAPT completed and reviewed
|  | Analyzed results and determine readiness for sign-off | Review Summary | Review completed and documented
|  | Secured formal approval from user for deployment | Sign-off Document | Sign-off received before deployment
|  | Captured defects and assess priority with stakeholders | Defect Log, Triage Notes | All defects triaged and prioritized
|  | Assigned, resolved, verified, and closed valid defects | Defect Resolution Sheet, Verification Log | 100% valid defects resolved and verified
|  | Reviewed and closed non-valid defects | Defect Closure Log | Invalid defects closed with justification
|  | Released changes post sign-off and verification | Deployment Logs | Deployment completed successfully
|  | Reviewed defect logs, closures, verifications, and process improvements | Review Summary Reports | Reviews completed at defined intervals

## Data
Status
Not started
In progress
Blocked
Done
N/A